## Sheet1
Sprint | Start | End | Epic | User Story | Task | Owner | Estimate(h) | Acceptance Criteria | Labels | Status | Area
Sprint 0 - Setup & Planning | 2025-10-23 | 2025-10-24 | Project Setup | As a dev, I need a clean structure. | Initialize GitHub repo, .gitignore, branch protection, feature-branch workflow | Leo | 2 | Repo has main/dev; branch rules active; PR required. | process,repo | Todo | Process
Sprint 0 - Setup & Planning | 2025-10-23 | 2025-10-24 | Environment | As a dev, I want backend ready. | Setup Express backend; add nodemon, CORS, dotenv; hello route | Zachary | 3 | `npm run dev` runs BE; GET /healthz returns 200. | backend,env | Todo | Backend
Sprint 0 - Setup & Planning | 2025-10-23 | 2025-10-24 | Environment | As a dev, I want frontend ready. | Setup SvelteKit app; sample routes; base layout | Steven | 3 | `npm run dev` runs FE; / shows starter page. | frontend,env | Todo | Frontend
Sprint 0 - Setup & Planning | 2025-10-23 | 2025-10-24 | Database | As a dev, I need DB ready. | Install SQLite; create db-init.sql; run connection test | Zachary | 3 | SQLite file created; script creates tables; connection ok. | backend,db | Todo | Backend
Sprint 0 - Setup & Planning | 2025-10-23 | 2025-10-24 | ERD / API | As a team, we need structure. | Draft ER diagram + routes.md (users/articles/comments/likes) | Leo | 2.5 | ERD + API doc merged to /docs. | docs,design | Todo | Process
Sprint 0 - Setup & Planning | 2025-10-23 | 2025-10-24 | CI / Docs | As a team, we need code standards. | Setup ESLint/Prettier/TS; GitHub Actions CI; CODEOWNERS | Steven | 2.5 | CI green on PR; lint/test gates enforced. | ci,quality | Todo | Process
Sprint 0 - Setup & Planning | 2025-10-23 | 2025-10-24 | Coordination | As a team, we plan ahead. | Finalize Agile Risk Plan & Sprint Backlog; add templates | Leo | 2 | Risk plan + backlog in /docs; issue/PR templates added. | process,docs | Todo | Process
Sprint 1 - Accounts Core | 2025-10-25 | 2025-10-27 | Authentication | As a visitor, I can register/login | POST /auth/register + /auth/login (bcrypt salt+hash, JWT) | Zachary | 6 | Register/Login success; passwords hashed; tokens issued. | backend,auth | Todo | Backend
Sprint 1 - Accounts Core | 2025-10-25 | 2025-10-27 | Authentication | As a user, I stay logged in | JWT middleware + protected route guard | Zachary | 3 | Protected routes return 401 without token; pass with token. | backend,auth | Todo | Backend
Sprint 1 - Accounts Core | 2025-10-25 | 2025-10-27 | Profile | As a user, I can edit profile | PATCH /users/:id (bio,name) + multer avatar upload | Zachary | 3 | Profile updates persist; avatar URL served; size limit enforced. | backend,users | Todo | Backend
Sprint 1 - Accounts Core | 2025-10-25 | 2025-10-27 | Frontend Auth | As a user, I can sign in/out | Svelte pages for Register/Login/Profile; form validation (no alert()) | Steven | 6 | Responsive forms; inline errors; success redirect. | frontend,auth,ui | Todo | Frontend
Sprint 1 - Accounts Core | 2025-10-25 | 2025-10-27 | State Mgmt | As a user, session persists | Svelte auth store; persist token; logout flow | Steven | 3 | Session persists across refresh; logout clears state. | frontend,auth | Todo | Frontend
Sprint 1 - Accounts Core | 2025-10-25 | 2025-10-27 | UX Detail | As a user, I see avatar instantly | Avatar upload preview/cancel/retry flow | Steven | 2.5 | Preview shows before upload; retry works. | frontend,profile,ui | Todo | Frontend
Sprint 1 - Accounts Core | 2025-10-25 | 2025-10-27 | Validation API | As a user, I know username availability | GET /users/check?username=... returns 200/409 | Steven | 2 | Debounced check; conflict shows helper text. | backend,frontend,users | Todo | Backend & Frontend
Sprint 1 - Accounts Core | 2025-10-25 | 2025-10-27 | Seed DB | As a marker, I can test quickly | Add two demo users in db-init.sql | Zachary | 2 | Seed users available; creds documented. | backend,db | Todo | Backend
Sprint 1 - Accounts Core | 2025-10-25 | 2025-10-27 | Integration Test | As a team, we validate login flow | Postman/Vitest tests for register/login + error cases | Leo | 3 | Tests pass in CI; artifacts stored. | test,ci | Todo | Process
Sprint 2 - Articles Core | 2025-10-28 | 2025-10-30 | Articles CRUD | As a user, I can manage my articles | Articles table + GET/POST/PUT/DELETE with ownership checks | Zachary | 6 | CRUD functional; 403 if not owner; unit tests. | backend,articles | Todo | Backend
Sprint 2 - Articles Core | 2025-10-28 | 2025-10-30 | Editor | As a user, I can format articles | Integrate TinyMCE (basic + lists); toolbar and sanitize | Steven | 5 | Bold/italic/underline/lists available; sanitized output. | frontend,editor,ui | Todo | Frontend
Sprint 2 - Articles Core | 2025-10-28 | 2025-10-30 | Images | As a user, I can upload images | Image upload API (multer); static /uploads; header & inline support | Zachary | 3 | Header image renders; inline images embedded via editor. | backend,images | Todo | Backend
Sprint 2 - Articles Core | 2025-10-28 | 2025-10-30 | Likes | As a user, I can like/unlike | Likes table + toggle endpoint + FE button + count | Steven | 4 | Unique per-user like; count updates; UX consistent. | frontend,backend,likes | Todo | Backend & Frontend
Sprint 2 - Articles Core | 2025-10-28 | 2025-10-30 | My Articles | As a user, I can view my posts | /me/articles endpoint + FE page with pagination | Steven | 3 | Only my posts listed; pagination works. | frontend,articles | Todo | Frontend
Sprint 2 - Articles Core | 2025-10-28 | 2025-10-30 | Docs | As a team, we keep docs fresh | Update API docs for articles/images/likes | Leo | 2 | README/API section updated; examples included. | docs | Todo | Process
Sprint 3 - Comments & Search | 2025-10-31 | 2025-11-03 | Comments | As a user, I can comment & reply | Comments table (parent_id) + endpoints; delete rules | Zachary | 5 | Nested replies supported; author & article-author delete. | backend,comments | Todo | Backend
Sprint 3 - Comments & Search | 2025-10-31 | 2025-11-03 | Comments UI | As a reader, I can browse threads | Recursive Svelte component (<svelte:self/>) + collapse/expand | Steven | 4 | Chronological + indented view; toggle visibility. | frontend,comments,ui | Todo | Frontend
Sprint 3 - Comments & Search | 2025-10-31 | 2025-11-03 | Search/Sort | As a reader, I can find content | Case-insensitive search; sort by title/user/date (single key) | Zachary | 4 | Query params implemented; FE controls intuitive. | backend,search | Todo | Backend
Sprint 3 - Comments & Search | 2025-10-31 | 2025-11-03 | Responsive UI | As a user, site works anywhere | Global responsive layout; accessibility pass; toast errors | Steven | 3 | Mobile/tablet/desktop ok; keyboard accessible. | frontend,ux,a11y | Todo | Frontend
Sprint 3 - Comments & Search | 2025-10-31 | 2025-11-03 | Testing | As a team, we ensure quality | API/component tests; minimal e2e; CI coverage threshold | Leo | 4 | CI green; coverage meets % target. | test,ci | Todo | Process
Sprint 4 - Admin & Polish | 2025-11-04 | 2025-11-05 | Admin API | As an admin, I can manage users | GET /api/users + DELETE /api/users/:id with admin check; /api/login¦logout | Zachary | 5 | 200/204/401/403 correct; cascade delete content. | backend,admin | Todo | Backend
Sprint 4 - Admin & Polish | 2025-11-04 | 2025-11-05 | Java Swing | As an admin, I can use GUI tool | JFrame: login/logout; JTable users; delete selected; async avatar fetch; MVC/Observer | Kevin | 10 | Meets CS718 requirements; UI state enabled/disabled. | swing,admin | Todo | Desktop App
Sprint 4 - Admin & Polish | 2025-11-04 | 2025-11-05 | Async Avatars | As an admin, I see avatars | HTTP fetch avatar thumbnail on row select (non-blocking) | Kevin | 2 | No UI freeze; avatar shown in JPanel. | swing,admin | Todo | Desktop App
Sprint 4 - Admin & Polish | 2025-11-04 | 2025-11-05 | Documentation | As a team, we deliver docs | Final README: setup/API/pages/Swing usage; risk plan | Leo | 3 | README complete; two demo accounts listed. | docs | Todo | Process
Sprint 4 - Admin & Polish | 2025-11-04 | 2025-11-05 | Presentation | As a team, we present clearly | Create 15-min slide/video; record demo; rehearse Q&A | Leo | 3 | Deck/video ready; 15 min timebox. | presentation | Todo | Process
Sprint 4 - Admin & Polish | 2025-11-04 | 2025-11-05 | Finalize | As users, we get a stable release | Bug triage; performance pass; code freeze; tag v1.0 | Leo, Steven, Zachary, Kevin | 6 | All critical bugs closed; main tagged v1.0. | release,quality | Todo | Process